## test_hierarchy_table
level | seq | lft | rgt | name | description | guid
1 | 1 | 1 | 2 | non-visible root | This is the root element of the document - all other | 6e66b70a-04d0-429f-ade7-39af3412f782

## daily_issues
level | seq | prio | status | tags | category | name | description | start_time | stop_time | planned_hours | actual_hours | owner | type | guid
1 | 9 | 1 | 03-wip | issue-tracker | issue-tracker | apply the model passing in the db-to-txt action | Apply the model passing by refdrence in the db-to-txt action. Validate the architecture approach - now it can be applied to all the actions. | 2018-01-28 11:45 | 2018-01-28 15:30 | 3.5 | 4 | ysg | 0 | 6e66b70a-04d0-429f-ade7-39af3412f783

## weekly_issues
level | seq | prio | status | tags | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours
1 | 9 | 1 | 03-wip | issue-tracker | issue-tracker | apply the interfaces for the most common methods in the perl code | applied to several | event | task | 2018-01-19 21:00 | 2018-01-21 21:00 | 1.5 | 0
1 | 19 | 2 | 07-qas | issue-tracker | issue-tracker | change the issue-tracker setup for code and data accessibility from host and vms | change the issue-tracker setup for code and data accessibility from host and vms Implement via symlink under /opt/csitea/issue-tracker Benefits - less work during publishing , can access both code and data via mac host's UI | ysg | task | 2017-10-03 08:16 |  | 1.33 | 0
1 | 9 | 4 | 07-qas | issue-tracker | issue-tracker | Change names of modules to reflect the Input-Output-Control-Module architecture | Change names of modules to reflect the Input-Output-Control-Module architecture | event | task | 2018-01-19 21:00 | 2018-01-21 21:00 | 1.5 | 0
1 | 9 | 4 | 07-qas | issue-tracker | issue-tracker | add interfaces for the most common methods in the perl code | Implement the SetGettable interface Implement the Autoloadable interface | event | task | 2018-01-19 21:00 | 2018-01-21 21:00 | 1.5 | 0
1 | 18 | 5 | 06-onhold | issue-tracker | issue-tracker | add load-meta-to-json action | add load-meta-to-json action | ysg | task |  |  | 10 | 2
1 | 19 | 5 | 07-qas | issue-tracker | issue-tracker | add unit tests for the "platform" modules | add unit tests for the "platform" modules : - Initaitor - Configurator - Dispatcher - Logger | ysg | task | 2017-10-03 08:16 |  | 1.33 | 0
1 | 29 | 8 | 03-act | issue-tracker | issue-tracker | clone a src issue-tracker daily dir into a tgt issue-tracker project daily dir | clone a src issue-tracker daily dir into a tgt issue-tracker project daily dir | ysg | task-ondemand |  |  | 2.5 | 0

## monthly_issues
id | level | seq | prio | status | tags | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours
170630 | 1 | 6 | 6 | 06-onhold | issue-tracker | issue-tracker | add load-meta-to-json action | add load-meta-to-json action | feature | ysg |  |  | 10 | 2
170814 | 1 | 8 | 8 | 02-todo | issue-tracker | issue-tracker | gsheet-to-db feature | implement read from google sheeet in issue-tracker for any issue--tracker project | feature | ysg | 2017-08-14 00:00 | 2017-08-30 19:30 | 3.5 | 0
170820 | 1 | 7 | 7 | 02-todo | issue-tracker | issue-tracker | publish all the issue-tracker events into the google sheet calendar | publish all the issue-tracker events into the google sheet calendar | feature | ysg |  |  | 30 | 0
171103 | 1 | 1 | 1 | 03-wip | issue-tracker | issue-tracker | implement mysql nested-set load | the isg-pub mysql nested-set load has been real time burner. implement mysql nested-set load by setting left_rank and right_rank into the hs: - add the id column | feature | ysg | 2017-10-03 08:16 |  | 1.33 | 0
171003 | 1 | 9 | 9 | 07-qas | issue-tracker | issue-tracker | add unit tests for the "platform" modules | add unit tests for the "platform" modules : - Initaitor - Configurator - Dispatcher - Logger | functionality | ysg | 2017-10-03 08:16 |  | 1.33 | 0
171004 | 1 | 11 | 11 | 09-done | issue-tracker | issue-tracker | change the issue-tracker setup for code and data accessibility from host and vms | change the issue-tracker setup for code and data accessibility from host and vms Implement via symlink under /opt/csitea/issue-tracker Benefits - less work during publishing , can access both code and data via mac host's UI | functionality | ysg | 2017-10-03 08:16 |  | 1.33 | 0
180109 | 1 | 5 | 5 | 07-qas | issue-tracker | issue-tracker | add interfaces for the most common methods in the perl code | Implement the SetGettable interface Implement the Autoloadable interface | event | ysg | 2018-01-19 21:00 | 2018-01-21 21:00 | 1.5 | 0
180110 | 1 | 4 | 4 | 03-wip | issue-tracker | issue-tracker | apply the interfaces for the most common methods in the perl code | applied to several | event | ysg | 2018-01-07 21:00 | 2018-01-21 21:00 | 1.5 | 0
180119 | 1 | 2 | 2 | 07-qas | issue-tracker | issue-tracker | Change names of modules to reflect the Input-Output-Control-Module architecture | Change names of modules to reflect the Input-Output-Control-Module architecture | event | ysg | 2018-01-19 21:00 | 2018-01-21 21:00 | 1.5 | 0
180123 | 1 | 10 | 10 | 09-done | issue-tracker | issue-tracker | solve the problem with the difficulty for accessing the daily xls and the configuration | solve the problem with the difficulty for accessing the daily xls and the configuration by moving the project under the home and shared folder ... | setup | ysg |  |  | 1 | 1
180203 | 1 | 3 | 3 | 03-wip | issue-tracker | issue-tracker | implement upsert for table with bigint id and uuid | Each commit should contain reference to the issue-id | event | ysg | 2018-02-03 21:00 | 2018-04-15 21:00 | 1.5 | 0

## yearly_issues
level | prio | status | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours
2 | 1 | 03-act | issue-tracker-bugs | keep the amount of bugs on monthly basis to less than 5 | keep the amount of bugs on monthly basis to less than 5 | activity | ysg | 2017-03-01 | 2017-12-31
2 | 2 | 03-wip | issue-tracker | achieve full compatibility with the IOCM architecture | achieve full compatibility with the Input-Output Control Module architecture | task | ysg | 2017-03-01 | 2017-12-31
2 | 4 | 03-act | issue-tracker | achieve simplistic design and ease to use | achieve simplistic design and ease to use | task | ysg | 2017-03-01 | 2017-12-31
2 | 4 | 03-act | issue-tracker-design | achieve simplistic design and ease to use | achieve simplistic design and ease to use | task | ysg | 2017-03-01 | 2017-12-31
2 | 5 | 03-act | issue-tracker-maintenance | keep minimalistic maintenance | keep minimalistic maintenance | task | ysg | 2017-12-31 | 2017-12-31
2 | 5 | 03-act | issue-tracker-system | scalability: operate more than 15 - 20 projects | operate more than 15 projects in production mode | task | ysg | 2017-11-01 | 2017-12-31
2 | 5 | 02-todo | issue-tracker-system | add web framework app layer | add web framework app layer | task | ysg | 2017-06-23 | 2017-12-31
2 | 5 | 02-todo | issue-tracker-features | implement 2 -> 7 -level nesting for all actions | implement 2 -> 7 -level nesting for all actions | task | ysg | 2017-10-01 | 2017-12-31
2 | 6 | 01-eval | issue-tracker-features | integration with google calendar | integration with google calendar | task | ysg | 2017-10-01 | 2017-12-31
2 | 6 | 03-wip | issue-tracker-features | port all the isg-pub MVP features to the issue-tracker | port all the isg-pub MVP features to the issue-tracker | features-set | ysg | 2017-10-01 | 2017-12-31

## quinquennially_issues
level | prio | status | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours
2 | 5 | 03-act | issue-tracker | 20 users for issue-tracker projects | aquire more than 20 users to feed in data of issue-tracker prjojects | goal | ysg | 2018-06-01 | 2019-01-01
2 | 5 | 03-act | issue-tracker | gain github popularity for the issue-tracker project | By achieving 10 stars and 5 pull requests | goal | ysg | 2018-06-01 | 2019-01-01

## decadally_issues
level | prio | status | category | name | description | owner | type | start_time | stop_time | planned_hours | actual_hours
2 | 4 | 03-act | issue-tracker-design | achieve simplistic design and ease to use | achieve simplistic design and ease to use | goal | ysg | 2017-03-01 | 2017-12-31

## questions
level | seq | prio | status | tags | category | name | description | solution_proposal | updated_by | owner
1 | 1 | 1 | 03-wip | issuee-tracker | issuee-tracker | how-to copy efficiently items rows froom one project to another | the copy of items data from one project to another includes the copying via ui ( google sheet , xls ) | so far via ui - in Excel use paste special, values , so that the formattig stays the same. After the upsert with guid's if an issue is trully portable than it could be tracked from different projects | ysg | ysg
1 | 1 | 1 | 02-todo | issuee-tracker | issuee-tracker | how-to copy autogenerated data | we know how-to copy the non-autogenerated data from src db to another , yet has to copy it with the autogenerated uuid's | _ | ysg | ysg

## problems
level | seq | prio | status | category | name | description | solution_proposal | updated_by | owner | parent_id
1 | 1 | 1 | 03-wip | georgievi-fina | manual formatting | too much time is burning the manual formatting of the google sheets … | yet once formatted obviously even on post via the api the formatting persists | ysg | ysg