## daily_issues
id | level | prio | status | category | name | description | start_time | stop_time | run_date | updated_by | owner | parent_id
1 | 2 | 4 | 09-done | issue-tracker-setup | configure the perltidy | configure the perltidy | 10:30 | 11:30 | 2017-06-22 | ysg | ysg
2 | 2 | 4 | 09-done | issue-tracker-features | add perltidy call during the check-perl-syntax call | add perltidy call during the check-perl-syntax | 13:30 | 15:30 | 2017-06-22 | ysg | ysg
3 | 2 | 4 | 09-done | issue-tracker-features | create an empty issue_tracker mojo app | create an empty issue_tracker mojo app | 15:30 | 15:45 | 2017-06-22 | ysg | ysg
4 | 2 | 4 | 02-todo | issue-tracker-features | add the mojo-hypnotoad-start action | add the mojo-hypnotoad-start action | 22:00 | 23:00 | 2017-06-22 | ysg | ysg
5 | 2 | 4 | 02-todo | issue-tracker-features | add the mojo-hypnotoad-stop action | add the mojo-hypnotoad-stop action | 22:00 | 23:00 | 2017-06-22 | ysg | ysg
6 | 2 | 4 | 02-todo | issue-tracker-features | add the mojo-morbo-start action | add the mojo-morbo-start action | 22:00 | 23:00 | 2017-06-22 | ysg | ysg
7 | 2 | 4 | 02-todo | issue-tracker-features | add the mojo-morbo-stop action | add the mojo-morbo-stop action | 22:00 | 23:00 | 2017-06-22 | ysg | ysg
8 | 2 | 4 | 02-todo | issue-tracker-features | update the DevOps guide on how-to start and stop the web app | update the DevOps guide on how-to start and stop the web app | 22:00 | 23:00 | 2017-06-22 | ysg | ysg

## weekly_issues
id | level | prio | status | category | name | description | start_time | stop_time | run_date | updated_by | owner | parent_id
0 | 2 | 0 | 09-done | csitea-issue-tracker-bugs | fix the duplication bug | fix the duplication bug | 2017-06-19 | 2017-06-25 | 2017-06-22 | ysg | ysg
1 | 2 | 1 | 09-done | csitea-issue-tracker-bugs | refactor the whole workflow | refactor the whole workflow | 2017-06-19 | 2017-06-25 | 2017-06-22 | ysg | ysg
2 | 2 | 2 | 09-done | csitea-issue-tracker-bugs | levels are lost during db-to-txt action call | levels are lost during db-to-txt action call | 2017-06-19 | 2017-06-25 | 2017-06-22 | ysg | ysg
9 | 2 | 4 | 09-done | issue-tracker-features | implement the gmail-txt-issues action | implement the gmail-txt-issues action | 2017-06-19 | 2017-06-25 | 2017-06-22 | ysg | ysg
4 | 2 | 4 | 02-todo | issue-tracker-features | add the mojo-hypnotoad-start action | add the mojo-hypnotoad-start action | 2017-06-22 | 2017-06-25 | 2017-06-22 | ysg | ysg
5 | 2 | 4 | 02-todo | issue-tracker-features | add the mojo-hypnotoad-stop action | add the mojo-hypnotoad-stop action | 2017-06-22 | 2017-06-25 | 2017-06-22 | ysg | ysg
6 | 2 | 4 | 02-todo | issue-tracker-features | add the mojo-morbo-start action | add the mojo-morbo-start action | 2017-06-22 | 2017-06-25 | 2017-06-22 | ysg | ysg
7 | 2 | 4 | 02-todo | issue-tracker-features | add the mojo-morbo-stop action | add the mojo-morbo-stop action | 2017-06-22 | 2017-06-25 | 2017-06-22 | ysg | ysg
8 | 2 | 4 | 02-todo | issue-tracker-features | update the DevOps guide on how-to start and stop the web app | update the DevOps guide on how-to start and stop the web app | 2017-06-22 | 2017-06-25 | 2017-06-22 | ysg | ysg

## monthly_issues
id | level | prio | status | category | name | description | start_time | stop_time | run_date | updated_by | owner | parent_id
0 | 2 | 4 | 07-qas | issue-tracker-design | xls as primary data storage usage | define "xls as primary data storage strategy", because the formatting of the xls takes too longer + the txt files are for quick and dirty tasks + sharing the basic info fo the tasks | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
1 | 2 | 4 | 02-todo | issue-tracker-design | create the userstories for the xls as the primary storage | create the userstories for the xls as the primary storage | 2017-07-23 | 2017-07-30 | 2017-06-22 | ysg | ysg
2 | 2 | 5 | 06-onhold | issue-tracker-bugs | the Txt parser is too picky with new lines | the Txt parser is too picky with new lines | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
3 | 2 | 5 | 09-done | issue-tracker-features | add separate table for each period | add separate table for each period | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
4 | 2 | 4 | 07-qas | issue-tracker-features | implement 2-level for the txt-to-db action | implement 2-level for the txt-to-db action | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
5 | 2 | 4 | 07-qas | issue-tracker-features | implement 2-level for the db-to-xls action | implement 2-level for the db-to-xls action | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
6 | 2 | 4 | 07-qas | issue-tracker-features | implement 2-level for the db-to-txt action | implement 2-level for the db-to-txt action | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
7 | 2 | 6 | 09-done | issue-tracker-bugs | fix the duplicates bug | fix the duplicates bug | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
8 | 2 | 6 | 09-done | issue-tracker-bugs | fix the & to html & conversion bug | fix the & to html & conversion bug | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
9 | 2 | 6 | 09-done | issue-tracker-bugs | categories are scrambled in monthly period | categories are scrambled in monthly period | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
10 | 2 | 1 | 09-done | issue-tracker-maintenance | achieve production stability for all the projects | achieve production stability for all the projects | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
11 | 2 | 5 | 03-diss | issue-tracker-features | foreach project configure proj_owner postgre user configuration | foreach project configure proj_owner postgre user configuration - diss too early in the development cycle for that | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
12 | 2 | 5 | 03-diss | issue-tracker-features | implement global trace_level in logging | implement global trace_level in logging. Disgarding for now - out of focus | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
13 | 2 | 4 | 07-qas | issue-tracker-features | implement 2-level hierarchy for all actions | implement 2-level hierarchy for all actions | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
14 | 2 | 4 | 07-qas | issue-tracker-features | implement 2-level for the xls-to-db action | implement 2-level for the xls-to-db action | 2017-06-01 | 2017-06-30 | 2017-06-22 | ysg | ysg
15 | 2 | 4 | 09-done | issue-tracker-features | implement the gmail-txt-issues action | implement the gmail-txt-issues action | 2017-06-12 | 2017-06-15 | 2017-06-22 | ysg | ysg
16 | 2 | 2 | 09-done | issue-tracker-features | add IssueTracker mojo app | add IssueTracker mojo app | 2017-06-22 | 2017-06-22 | 2017-06-22 | ysg | ysg
17 | 2 | 1 | 02-todo | issue-tracker-features | add the start , stop actions to the IssueTracker mojo app + documentation | add the start , stop actions to the IssueTracker mojo app + documentation | 2017-06-22 | 2017-06-22 | 2017-06-22 | ysg | ysg

## yearly_issues
id | level | prio | status | category | name | description | start_time | stop_time | run_date | updated_by | owner | parent_id
11 | 2 | 1 | 03-act | issue-tracker-maintenance | achieve minimalistic maintenance | achieve minimalistic maintenance | 2017-12-31 | 2017-12-31 | 2017-06-11 | ysg | ysg
12 | 2 | 1 | 03-act | issue-tracker-system | scalability: operate more than 15 - 20 projects | operate more than 15 projects in production mode | 2017-11-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
15 | 2 | 1 | 03-act | issue-tracker-system | scalability: operate in prod 01-15 projects | scalability: operate in prod 01-15 projects | 2017-03-01 | 2017-11-01 | 2017-06-11 | ysg | ysg
1 | 2 | 4 | 03-act | issue-tracker-design | achieve simplistic design and ease to use | achieve simplistic design and ease to use | 2017-03-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
2 | 2 | 4 | 09-qa | issue-tracker-features | implement 2-level nesting for all actions | implement 2-level nesting for all actions | 2017-03-01 | 2017-10-01 | 2017-06-11 | ysg | ysg
17 | 2 | 4 | 07-qas | issue-tracker-features | implement the gmail-txt-issues action | implement the gmail-txt-issues action | 2017-06-12 | 2017-06-15 | 2017-06-10 | ysg | ysg
3 | 2 | 5 | 03-act | issue-tracker-bugs | keep the amount of bugs on monthly basis to less than 5 | keep the amount of bugs on monthly basis to less than 5 | 2017-03-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
5 | 2 | 5 | 09-done | issue-tracker-features | add the txt-to-db and db-to-xls action | add the txt-to-db and db-to-xls action | 2017-03-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
6 | 2 | 5 | 09-done | issue-tracker-features | add the xls-to-db and db-to-txt action | add the xls-to-db and db-to-txt action | 2017-03-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
9 | 2 | 5 | 07-qas | issue-tracker-features | add issues sorting by any attribute for any action | add issues sorting by any attribute for any action | 2017-12-31 | 2017-12-31 | 2017-06-11 | ysg | ysg
10 | 2 | 5 | 07-qas | issue-tracker-features | implement daily handling of issues, notes , cheatsheets and input xls for mulitple projects | implement daily handling of issues, notes , cheatsheets and input xls for mulitple projects | 2017-12-31 | 2017-12-31 | 2017-06-11 | ysg | ysg
13 | 2 | 5 | 02-todo | issue-tracker-system | add web framework app layer | add web framework app layer | 2017-06-23 | 2017-12-31 | 2017-06-11 | ysg | ysg
14 | 2 | 5 | 02-todo | issue-tracker-system | start combining isg-pub and issue - tracker | start combining isg-pub and issue - tracker | 2017-10-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
16 | 2 | 5 | 02-todo | issue-tracker-features | implement 2 -> 7 -level nesting for all actions | implement 2 -> 7 -level nesting for all actions | 2017-10-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
7 | 2 | 6 | 01-eval | issue-tracker-features | integration with google calendar | integration with google calendar | 2017-10-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
8 | 2 | 6 | 02-todo | issue-tracker-features | integration with isg-pub | integration with isg-pub | 2017-10-01 | 2017-12-31 | 2017-06-11 | ysg | ysg