## monthly_issues
id | level | prio | status | category | name | description | start_time | stop_time | run_date | updated_by | owner | parent_id
11 | 2 | 5 | 03-diss | issue-tracker-features | foreach project configure proj_owner postgre user configuration | foreach project configure proj_owner postgre user configuration - diss too early in the development cycle for that | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
12 | 2 | 5 | 03-diss | issue-tracker-features | implement global trace_level in logging | implement global trace_level in logging. Disgarding for now - out of focus | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
2 | 2 | 5 | 06-onhold | issue-tracker-bugs | the Txt parser is too picky with new lines | the Txt parser is too picky with new lines | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
0 | 2 | 4 | 07-qas | issue-tracker-design | xls as primary data storage usage | define "xls as primary data storage strategy", because the formatting of the xls takes too longer + the txt files are for quick and dirty tasks + sharing the basic info fo the tasks | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
4 | 2 | 4 | 07-qas | issue-tracker-features | implement 2-level for the txt-to-db action | implement 2-level for the txt-to-db action | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
5 | 2 | 4 | 07-qas | issue-tracker-features | implement 2-level for the db-to-xls action | implement 2-level for the db-to-xls action | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
6 | 2 | 4 | 07-qas | issue-tracker-features | implement 2-level for the db-to-txt action | implement 2-level for the db-to-txt action | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
13 | 2 | 4 | 07-qas | issue-tracker-features | implement 2-level hierarchy for all actions | implement 2-level hierarchy for all actions | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
14 | 2 | 4 | 07-qas | issue-tracker-features | implement 2-level for the xls-to-db action | implement 2-level for the xls-to-db action | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
10 | 2 | 1 | 09-done | issue-tracker-maintenance | achieve production stability for all the projects | achieve production stability for all the projects | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
7 | 2 | 6 | 09-done | issue-tracker-bugs | fix the duplicates bug | fix the duplicates bug | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
8 | 2 | 6 | 09-done | issue-tracker-bugs | fix the & to html & conversion bug | fix the & to html & conversion bug | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
9 | 2 | 6 | 09-done | issue-tracker-bugs | categories are scrambled in monthly period | categories are scrambled in monthly period | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
3 | 2 | 5 | 09-done | issue-tracker-features | add separate table for each period | add separate table for each period | 2017-06-01 | 2017-06-30 | 2017-06-10 | ysg | ysg
15 | 2 | 4 | 09-done | issue-tracker-features | implement the gmail-txt-issues action | implement the gmail-txt-issues action | 2017-06-12 | 2017-06-15 | 2017-06-10 | ysg | ysg
1 | 2 | 4 | 02-todo | issue-tracker-design | create the userstories for the xls as the primary storage | create the userstories for the xls as the primary storage | 2017-07-23 | 2017-07-30 | 2017-06-10 | ysg | ysg