## yearly_issues
id | level | prio | status | category | name | description | start_time | stop_time | run_date | updated_by | owner | parent_id
11 | 2 | 1 | 03-act | issue-tracker-maintenance | achieve minimalistic maintenance | achieve minimalistic maintenance | 2017-12-31 | 2017-12-31 | 2017-06-11 | ysg | ysg
12 | 2 | 1 | 03-act | issue-tracker-system | scalability: operate more than 15 - 20 projects | operate more than 15 projects in production mode | 2017-11-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
15 | 2 | 1 | 03-act | issue-tracker-system | scalability: operate in prod 01-15 projects | scalability: operate in prod 01-15 projects | 2017-03-01 | 2017-11-01 | 2017-06-11 | ysg | ysg
1 | 2 | 4 | 03-act | issue-tracker-design | achieve simplistic design and ease to use | achieve simplistic design and ease to use | 2017-03-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
2 | 2 | 4 | 09-qa | issue-tracker-features | implement 2-level nesting for all actions | implement 2-level nesting for all actions | 2017-03-01 | 2017-10-01 | 2017-06-11 | ysg | ysg
17 | 2 | 4 | 07-qas | issue-tracker-features | implement the gmail-txt-issues action | implement the gmail-txt-issues action | 2017-06-12 | 2017-06-15 | 2017-06-10 | ysg | ysg
3 | 2 | 5 | 03-act | issue-tracker-bugs | keep the amount of bugs on monthly basis to less than 5 | keep the amount of bugs on monthly basis to less than 5 | 2017-03-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
5 | 2 | 5 | 09-done | issue-tracker-features | add the txt-to-db and db-to-xls action | add the txt-to-db and db-to-xls action | 2017-03-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
6 | 2 | 5 | 09-done | issue-tracker-features | add the xls-to-db and db-to-txt action | add the xls-to-db and db-to-txt action | 2017-03-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
9 | 2 | 5 | 07-qas | issue-tracker-features | add issues sorting by any attribute for any action | add issues sorting by any attribute for any action | 2017-12-31 | 2017-12-31 | 2017-06-11 | ysg | ysg
10 | 2 | 5 | 07-qas | issue-tracker-features | implement daily handling of issues, notes , cheatsheets and input xls for mulitple projects | implement daily handling of issues, notes , cheatsheets and input xls for mulitple projects | 2017-12-31 | 2017-12-31 | 2017-06-11 | ysg | ysg
13 | 2 | 5 | 02-todo | issue-tracker-system | add web framework app layer | add web framework app layer | 2017-06-23 | 2017-12-31 | 2017-06-11 | ysg | ysg
14 | 2 | 5 | 02-todo | issue-tracker-system | start combining isg-pub and issue - tracker | start combining isg-pub and issue - tracker | 2017-10-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
16 | 2 | 5 | 02-todo | issue-tracker-features | implement 2 -> 7 -level nesting for all actions | implement 2 -> 7 -level nesting for all actions | 2017-10-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
7 | 2 | 6 | 01-eval | issue-tracker-features | integration with google calendar | integration with google calendar | 2017-10-01 | 2017-12-31 | 2017-06-11 | ysg | ysg
8 | 2 | 6 | 02-todo | issue-tracker-features | integration with isg-pub | integration with isg-pub | 2017-10-01 | 2017-12-31 | 2017-06-11 | ysg | ysg